WE Strategic Planning Process (Draft, Sept. 16, 2020)

|  |  |
| --- | --- |
| WE Board Meeting: Present draft plan for strategic planning to Board for feedback | Sept. 16, 2020 |
| Post plan for strategic planning on website with links to materials, including organizational history, previous strategic plans, and antiracism guiding principles and practices | Sept. 30, 2020 |
| WE Program: WE membership survey presentation and panel discussion*\*Preview town hall event and introduce pathways for members to engage with strategic planning*  | Oct. 16, 2020 |
| WE Board Meeting: Vision and future direction discussion | Oct. 21, 2020 |
| Member/Community Engagement activities | TBD |
| WE Board Virtual Retreat: Finalize strategic framework (i.e., strategic goals and objectives), followed by goal team meetings to finalize strategies*Invite 2021 board members to participate (optional)* | TBD |
| WE Board Meeting: Initial strategic plan draft for discussion/review | TBD |
| WE Board Meeting: Strategic plan draft for board reviewOpportunity for member comments following board meeting | TBD |
| WE Board Meeting: Strategic plan for board vote | TBD |
| WE Board Meeting: 2021 action plan development for discussion | TBD |
| WE Board Meeting: 2021 action plan draft for approval | TBD |